## Slide 1
VALUE STREAM MAPPING
Preparing for a Home Baseball Game
Current State → Lean Metrics → Future State
Visualize
Analyze
Optimize
Goal: have the field, equipment, coaches, and players ready for first pitch with less wasted time and a better pregame buffer.
Brady Heinz | Module 5.2 Assignment | 1

## Slide 2
Current-State Value Stream
The existing process is modeled primarily as sequential work.
Field Prep
45 min
Bases & Lines
20 min
Scoreboard & Rosters
15 min
Equipment Setup
15 min
Batting Practice
45 min
Field Touch-Up
10 min
Team Warmup
20 min
Final Meeting
10 min
Estimated Current Cycle Time
180 minutes = 3 hours
Main issue: tasks that can be done by different people are waiting on one another instead of occurring in parallel.
Brady Heinz | Module 5.2 Assignment | 2

## Slide 3
Lean Metrics & Waste Analysis
Cycle time shows the total pregame process; flow time shows where the time is being spent.
Activity | Flow Time | Lean Observation
Field preparation | 45 min | Necessary work
Bases and lines | 20 min | Necessary work
Scoreboard and rosters | 15 min | Can overlap
Equipment setup | 15 min | Can overlap
Batting practice | 45 min | Necessary work
Final field touch-up | 10 min | Necessary after BP
Team warmup | 20 min | Necessary work
Final meeting / lineup exchange | 10 min | Necessary work
Activity
Flow Time
Lean Observation
Waste Identified
Waiting caused by doing independent tasks sequentially.
Improvement Opportunity
Assign field crew, coaches, and players separate responsibilities so multiple activities can happen at the same time.
Brady Heinz | Module 5.2 Assignment | 3

## Slide 4
Future-State Value Stream
Parallel work reduces waiting while keeping the important baseball activities intact.
FIELD CREW
0–45
Prepare field & mound
45–65
Bases & chalk lines
65–110
Monitor field
110–120
Final touch-up
120–150
Final field check
COACH / ASSISTANT
0–45
Scoreboard + roster
45–65
Finish lineup
65–110
Run batting practice
110–120
Prepare defense
120–140
Team warmup
140–150
Meeting / lineup exchange
PLAYERS
0–45
Equipment setup
45–65
Warmup / BP setup
65–110
Batting practice
110–120
Finish BP
120–140
Team warmup
140–150
Team meeting
Brady Heinz | Module 5.2 Assignment | 4

## Slide 5
Optimized Results
The future-state process focuses on eliminating waiting and standardizing responsibilities.
Current Cycle Time
180 min
3 hr
Future Cycle Time
150 min
2 hr 30 min
Time Saved
30 min
per home game
Cycle-Time Reduction
16.7%
improvement
Optimization Plan
Assign responsibilities before each home game: field crew, coach/assistant, and players.
Complete scoreboard, roster, and equipment setup while field preparation is underway.
Use a standard pregame checklist so important tasks are not duplicated or forgotten.
Use the 30-minute improvement as additional preparation/buffer time for weather, field, equipment, or scoreboard problems.
Result: a more predictable, organized, and efficient path to first pitch.
Brady Heinz | Module 5.2 Assignment | 5